## Calculator
Sizing estimation for a single Automation
Instructions:
1. Determine the complexity of the project by going through the attributes 1 - 5 below
2. Select the appropriate response from the XS, S, M, L and XL quadrants. Only one X per row is allowed.
3. After all responses have been provided, pre-defined rules will determine the complexity of the project. Refer to cell F19 to confirm project complexity
4. If your scenario exceeds the parameter given, consult a Tech Lead for separate sizing since additional development hrs might be required.
COMPLEXITY ATTRIBUTES
|  | XS to be used for corrections on existing automations or for small scale automations (RDA, macros, etc.) no more than 2 parameters from below list can be selected for XS size | X |  | S | X |  | M | X |  | L | X |  | XL | X |  | Weighting Criteria S | Weighting Criteria M | Weighting Criteria L | Weighting Criteria XL
1 | #1 | Number of activities in the process to be automated is < 10 Description: Activity is a piece of work that forms one logical step within a process. That activity could be subdivided into several keystrokes, therefore on average it would contain up to 10 keystrokes. The Activity is done in a single application |  |  | Number of activities in the process to be automated is < 10 Description: Activity is a piece of work that forms one logical step within a process. That activity could be subdivided into several keystrokes, therefore on average it would contain up to 10 keystrokes. The Activity is done in a single application |  |  | Number of activities in the process to be automated is between 11 and 20 Description: Activity is a piece of work that forms one logical step within a process. That activity could be subdivided into several keystrokes, therefore on average it would contain up to 10 keystrokes. The Activity is done in a single application |  |  | Number of activities in the process to be automated is between 21 and 40 Description: Activity is a piece of work that forms one logical step within a process. That activity could be subdivided into several keystrokes, therefore on average it would contain up to 10 keystrokes. The Activity is done in a single application |  |  | Number of activities in the process to be automated is between 41 and 60 Description:: Activity is a piece of work that forms one logical step within a process. That activity could be subdivided into several keystrokes, therefore on average it would contain up to 10 keystrokes. The Activity is done in a single application | X | 8 | 2 | 4 | 6 | 8 | Equivalence Chart
1 | #2 | Business Rules - zero business rules which result in a new flow. Description: Business Rule which results in creation of additional flow(i.e. go to additional SAP transaction) should contain more than 2 activities. |  |  | Business Rules - zero business rules which result in a new flow. Description: Business Rule which results in creation of additional flow(i.e. go to additional SAP transaction) should contain more than 2 activities. |  |  | Business Rules - 1-2 business rules which result in a new flow. Description: Business Rule which results in creation of additional flow(i.e. go to additional SAP transaction) should contain more than 2 activities. |  |  | Business Rules - 3-4 business rules which result in a new flow. Description: Business Rule which results in creation of additional flow(i.e. go to additional SAP transaction) should contain more than 2 activities. |  |  | Business Rules - 5-6 business rules which result in a new flow. Description: Business Rule which results in creation of additional flow(i.e. go to additional SAP transaction) should contain more than 2 activities. | X | 8 | 2 | 4 | 6 | 8 | 7 | 8 | S
1 | #3 | Number of digital layouts (templates) to be used by RPA is 1 Description: Any different input/output file should be treated as separate layouts. This can relate to different digital file extensions (e.g. pdf, xls) or it can be different templates within one file extension (e.g. Month End Reconciliation Report, Approval Matrix) |  |  | Number of digital layouts (templates) to be used by RPA is 1 Description: Any different input/output file should be treated as separate layouts. This can relate to different digital file extensions (e.g. pdf, xls) or it can be different templates within one file extension (e.g. Month End Reconciliation Report, Approval Matrix) |  |  | Number of digital layouts (templates) to be used by RPA is 2-3 Description: Any different input/output file should be treated as separate layouts. This can relate to different digital file extensions (e.g. pdf, xls) or it can be different templates within one file extension (e.g. Month End Reconciliation Report, Approval Matrix) |  |  | Number of digital layouts (templates) to be used by RPA is 4-6 Description:Any different input/output file should be treated as separate layouts. This can relate to different digital file extensions (e.g. pdf, xls) or it can be different templates within one file extension (e.g. Month End Reconciliation Report, Approval Matrix) | X | 3 | Number of digital layouts (templates) to be used by RPA is 7-10 Description: Any different input/output file should be treated as separate layouts. This can relate to different digital file extensions (e.g. pdf, xls) or it can be different templates within one file extension (e.g. Month End Reconciliation Report, Approval Matrix) |  |  | 1 | 2 | 3 | 4 | 9 | 15 | M
1 | #4 | Requirement to interface with only 1-2 target applications/interfaces Description: Target application used by the business to perform daily duties, any application/interface should be considered separately, eg SAP, Nakisa, Excel, Outlook |  |  | Requirement to interface with only 1-2 target applications/interfaces Description: Target application used by the business to perform daily duties, any application/interface should be considered separately, eg SAP, Nakisa, Excel, Outlook | X | 1 | Requirement to interface with only 3 - 4 target applications/interfaces Description: Target application used by the business to perform daily duties, any application/interface should be considered separately, eg SAP, Nakisa, Excel, Outlook |  |  | Requirement to interface with only target 5-6 applications/interfaces Description: Target application used by the business to perform daily duties, any application/interface should be considered separately, eg SAP, Nakisa, Excel, Outlook |  |  | Requirement to interface with only target 7-8 applications/interfaces Description: Target application used by the business to perform daily duties, any application/interface should be considered separately, eg SAP, Nakisa, Excel, Outlook |  |  | 1 | 2 | 3 | 4 | 16 | 22 | L
1 | #5 | Additional Technology in scope - none Description: Requirement of surface automation/Citrix, web services or API to be developed. **If there is a need to integrate already existing Python/VBA macros into the RPA solution(e.g. include/adjust already created macro into Blue Prism code stage or develop Python/VBA macros outside of RPA solution - like VBA Macro to validate input file) it should be considered as additional technology in scope |  |  | Additional Technology in scope - none Description: Requirement of surface automation/Citrix, web services or API to be developed. **If there is a need to integrate already existing Python/VBA macros into the RPA solution(e.g. include/adjust already created macro into Blue Prism code stage or develop Python/VBA macros outside of RPA solution - like VBA Macro to validate input file) it should be considered as additional technology in scope | X | 1 | Additional Technology in scope - 1 Description: Requirement of surface automation/Citrix, web services or API to be developed. **If there is a need to integrate already existing Python/VBA macros into the RPA solution(e.g. include/adjust already created macro into Blue Prism code stage or develop Python/VBA macros outside of RPA solution - like VBA Macro to validate input file) it should be considered as additional technology in scope |  |  | Additional Technology in scope - 2-3 Description: Requirement of surface automation/Citrix, web services or API to be developed. *If there is a need to integrate already existing Python/VBA macros into the RPA solution(e.g. include/adjust already created macro into Blue Prism code stage or develop Python/VBA macros outside of RPA solution - like VBA Macro to validate input file) it should be considered as additional technology in scope |  |  | Additional Technology in scope - 4-5 Description: Requirement of surface automation/Citrix, web services or API to be developed. *If there is a need to integrate already existing Python/VBA macros into the RPA solution(e.g. include/adjust already created macro into Blue Prism code stage or develop Python/VBA macros outside of RPA solution - like VBA Macro to validate input file) it should be considered as additional technology in scope |  |  | 1 | 2 | 3 | 4 | 23 | 28 | XL
0
0 |  |  | 0 | 0 |  | 2 | 2 |  | 0 | 0 |  | 1 | 3 |  | 2 | 16
0
1 |  | Score |  |  | 21 |  |  |  | 0
|  | Project Classification |  |  | L
Effort estimates in days from Define to Deploy
* Estimation of the effort needed from BA/Developer side to complete all the required activities in the relevant phase
Actual timeline of the output delivery (per the phase) depends on the availability of the respective resources on PMI side (Business representatives)
Phase |  | XS |  |  | S |  |  | M |  |  | L |  |  | XL
Define * |  | 3 |  |  | 7 - 15 |  |  | 15 |  |  | 20 |  |  | 25
Design & Build |  | 5 |  |  | 8 - 15 |  |  | 25 |  |  | 30 |  |  | 40
UAT * |  | 1 |  |  | 3 - 5 |  |  | 5 |  |  | 5 |  |  | 10
Deploy * |  | 1 |  |  | 2 - 5 |  |  | 5 |  |  | 5 |  |  | 5
Total days |  | 10 |  |  | 20 - 40 |  |  | 50 |  |  | 60 |  |  | 80
2-weeks spritns |  | 1 |  |  | 2 - 4 |  |  | 5 |  |  | 6 |  |  | 8
Macro for validation
Applications: | GMP, Excel
Total | 2
Steps
(Sheet "Steps")
Total | 52
Business Rules
Change description
Change approval rights & Add signatory / Change limit / limit & rights
Replace signatory/Owner & signatory / Copy ASM access
Replace object owner
Remove signatory
Delete object
Total | 6
Layouts:
Input template: Modify
Input template: Simple mass change
Input template: Delete object
Schema file
CSV objects + csv signatories
Total | 4-6
Additional Technology in scope
Total | 0

## Steps
Modify
| Step description | Step weight | Comment about reusability
| Search for modification request in template | 1
| Recognize and take first/next request for processing | 2
| Type of request: Change description | 0.5
| Type of request: Change approval rights | 0.5
| Type of request: Add signatory / Change limit / limit & rights | 0.5
| Type: Replace signatory/Owner & signatory / Copy ASM access | 0.5
| Type: Replace object owner | 0.5
| Type: Remove signatory | 0.5
Change descr | Go to t-code ZDIASMDIA, find object to be updated | 0.5 | Partial reusability from creation
| Download CSV file for object | 0 | Reusability from creation
| Update object file with new description | 1
| Upload csv file object | 0 | Reusability from creation
| Read status for object upload | 0.5 | Partial reusability from creation
| Activate | 0 | Reusability from creation
| Update processing status for request in template | 1
Change approval rights & Add signatory / Change limit / limit & rights | Verify approver hierarchical layer | 0.5 | Partial reusability
| Confirm if approver assigned according to schema | 0.5 | Partial reusability
| Go to t-code ZDIASMDIA, find object to be updated | 0.5 | Partial reusability
| Download CSV file for object and signatory | 0 | Reusability from creation
| Update signatories csv file | 2 | Various update needed for each from 4 action requested
| Verify and adjust "PO owner" flag for signatory | 1 | By each acion type the same step name will require different checks
| Upload csv file signatories | 0 | Reusability
| Read status for signatories upload | 0.5 | Partial reusability from creation
| Activate | 0 | Reusability from creation
| Update processing status for request in template | 0 | Reusability
Replace signatory/Owner & signatory / Copy ASM access | Verify approver hierarchical layer | 0 | Reusability
| Check if new user should have the same level and rigts | 1
| Confirm if approver assigned according to schema | 0 | Reusability
| Go to t-code ZDIASMDIA, find object to be updated | 0.5 | Partial reusability
| Download CSV file for object and signatory | 0 | Reusability
| Confirm correctness of new signatory level | 1
| Enter mass change t-code and provide proper parameters | 2 | various parameters based on action
| Process replacement action | 1
| Go to t-code ZDIASMDIA, find object to be updated | 0 | Reusability
| Download CSV file for object and signatory | 0 | Reusability
| Any replacement unsuccessful? | 1
| Check which update was not successful | 1
| Update processing status for failed items | 1
| Filter on successfully changed items | 1
| Update for signatory limit & rights required? | 1
| Type of change required | 0.5 | Partial reusability
| Activate | 0 | Reusability
| Update processing status for request in template | 0 | Reusability
Replace object owner | Go to t-code ZDIASMDIA, find object to be updated | 0.5 | Partial reusability
| Download CSV file for object and signatory | 0 | Reusability
| Update csv file for object and save | 0.5 | Partial reusability
| Update for signatory limit & rights required? | 0 | Reusability
| Update csv file for signatory | 0.5 | Partial reusability
| Signatory exists in structure? | 1
| Update processing status for incorrect request | 0.5 | Partial reusability
| Verify and adjust "PO owner" flag for signatory | 1 | By each acion type the same step name will require different checks
| Upload csv file object | 0 | Reusability
| Read status for object upload | 0 | Reusability
| Upload for signatories required? | 1
| Upload csv file signatories | 0 | Reusability
| Read status for signatories upload | 0 | Reusability
| Activate | 0 | Reusability
| Update processing status for request in template | 0 | Reusability
Remove signatory | Go to t-code ZDIASMDIA, find object to be updated | 0.5 | Partial reusability
| Download CSV file for object and signatory | 0 | Reusability
| Check if user is not object owner as well | 1
| Verify and adjust "PO owner" flag for signatory | 1 | By each acion type the same step name will require different checks
| PO owner flag needs to be updated? | 1
| Update csv file for signatory | 0.5 | Partial reusability
| Upload csv file signatories | 0 | Reusability
| Read status for signatories upload | 0 | Reusability
| Activate | 0 | Reusability
| Enter mass change t-code and provide proper parameters | 1 | various parameters based on action
| Process Remove action | 0.5 | Partial reusability
| Removal fully successful | 0.5 | Partial reusability
| Activate | 0 | Reusability
| Update processing status for request in template | 0 | Reusability
| Go to t-code ZDIASMDIA, find object to be updated | 0 | Reusability
| Download CSV file for object and signatory | 0 | Reusability
| Check which update was not successful | 0.5 | Partial reusability
| Filter on successfully changed items | 0.5 | Partial reusability
| Any removal successful? | 0.5
| Next modification request in template? | 1
38.5
| TOTAL | 38.5

## Feature and delivery timeline
PROJECT TITLE | EXPOSURE
SQUAD | MASTER DATA
BUSINESS ANALYST | IRENA SCHNOBER
DEVELOPER | HEMALATHA POLASANI
| SP [TASKS COUNT] |  |  | SP [TASKS COUNT]
TOTAL SP | 21.4 SP [28 TASKS] | SP COMPLETION | TOTAL SP | 21.4 SP [29 TASKS] | SP COMPLETION
COMPLETED | 12.6 SP [16 TASKS] | 58.88% | APPROVED | 21.4 SP [28 TASKS] | 100%
IN RPOGRESS | 0 SP [0 TASKS] | 0% | REJECTED | 0 SP [0 TASKS] | 0%
NOT STARTED | 0 SP [0 TASKS] | 41.12% | PENDING | 0 SP [0 TASKS] | 0%
| SP [TASKS COUNT] | SP COMPLETION
MUST | 21.4 SP [29 TASKS] | 100%
SHOULD | 0 SP [0 TASKS] | 0%
1 hour = | 0.0666 | points
FEATURE | SCOPE | ACCEPTANCE STATUS | Start date | End date | SP | Hours | Developer | PRIORITY | COMPLETION % | DEVELOPMENT STATUS | REVIEWER | PEER REVIEW STATUS | REMARKS
Main Page | ORIGINAL | APPROVED | 2021-07-09 | 2021-08-27 | 0.6 | 9 | Hemalatha Polasani | MUST | 70% | IN PROGRESS
Modify ASM Intial check and action Change Description | ORIGINAL | APPROVED | 2021-07-12 | 2021-07-12 | 0.6 | 9 | Hemalatha Polasani | MUST | 100% | COMPLETED |  |  | Waiting for test data
Modify Object : SAP t-code ZDIASMDIA and ZDIASMUPL | ORIGINAL | APPROVED | 2021-07-13 | 2021-07-13 | 0.6 | 9 | Hemalatha Polasani | MUST | 100% | COMPLETED
Add Signatory action and verify and adjust PO owner flag | ORIGINAL | APPROVED | 2021-07-14 | 2021-07-16 | 1.6 | 24 | Hemalatha Polasani | MUST | 100% | COMPLETED
Change Approval Rights | ORIGINAL | APPROVED | 2021-07-16 | 2021-07-19 | 0.6 | 9 | Hemalatha Polasani | MUST | 100% | COMPLETED
Change Approval Limit | ORIGINAL | APPROVED | 2021-07-20 | 2021-07-21 | 0.6 | 9 | Hemalatha Polasani | MUST | 100% | COMPLETED
Change Approver limit and rights | ORIGINAL | APPROVED | 2021-07-21 | 2021-07-21 | 0.6 | 9 | Hemalatha Polasani | MUST | 100% | COMPLETED
Replace Signatory : 1.check if signatory is not object owner as well and 2.check if signatory should be changed for limit | ORIGINAL | APPROVED | 2021-07-22 | 2021-07-23 | 1.2 | 18 | Hemalatha Polasani | MUST | 90% | COMPLETED
Business demo | ORIGINAL | APPROVED | 2021-07-26 | 2021-07-26 | 0.6 | 9 | Hemalatha Polasani | MUST | 100% | COMPLETED
Replace Signatory : 3. Confirm correctness of new signatory level vs old one | ORIGINAL | APPROVED | 2021-07-27 | 2021-07-27 | 0.6 | 9 | Hemalatha Polasani | MUST | 90% | COMPLETED
Object Creation : SAP t-code ZDIASMMASS | ORIGINAL | APPROVED | 2021-07-28 | 2021-07-29 | 1.2 | 18 | Hemalatha Polasani | MUST | 100% | COMPLETED
Replace Signatory: 4. Process replacement action and Integrate object with process and 5. Update to new signatory limit/rights required? | ORIGINAL | APPROVED | 2021-07-30 | 2021-08-02 | 1.2 | 18 | Hemalatha Polasani | MUST | 90% | COMPLETED
Integrating all new steps with resuable steps for replace signatory | ORIGINAL | APPROVED | 2021-08-03 | 2021-08-03 | 0.6 | 9 | Hemalatha Polasani | MUST | 90% | COMPLETED
Replace object owner with existing signatory | ORIGINAL | APPROVED | 2021-08-04 | 2021-08-04 | 0.6 | 9 | Hemalatha Polasani | MUST | 90% | COMPLETED
Replace object owner and signatory | ORIGINAL | APPROVED | 2021-08-05 | 2021-08-05 | 0.6 | 9 | Hemalatha Polasani | MUST | 90% | COMPLETED
Remove Signatory : 1. Process remove action | ORIGINAL | APPROVED | 2021-08-06 | 2021-08-18 | 0.8 | 12 | Hemalatha Polasani | MUST | 90% | COMPLETED
Delay |  |  | 2021-08-09 | 2021-08-17 | 0 |  |  | MUST |  |  |  |  | Delayed as taken sick leave
Simple Mass Change Initial Check and Replace Signatory : 1. Check if replacement was successful for all objects | ORIGINAL | APPROVED | 2021-08-19 | 2021-08-20 | 1.2 | 18 | Hemalatha Polasani | MUST | 80% | IN PROGRESS
Import code to SBX and bug fixes | ORIGINAL | APPROVED | 2021-08-19 | 2021-08-23 | 0.4 | 6 | Hemalatha Polasani | MUST | 80% | IN PROGRESS |  |  | SBX testing analysing issues and fixing them
Replace object owner with existing signatory : 1. Check if new object owner exists in ASM structure | ORIGINAL | APPROVED | 2021-08-23 | 2021-08-24 | 1.2 | 18 | Hemalatha Polasani | MUST | 80% | IN PROGRESS
Business demo | ORIGINAL | APPROVED | 2021-08-25 | 2021-08-25 | 0.6 | 9 | Hemalatha Polasani | MUST | 100% | COMPLETED |  |  | Delayed as per client availability
Replace object owner and signatory | ORIGINAL | APPROVED | 2021-08-26 | 2021-08-26 | 0.6 | 9 | Hemalatha Polasani | MUST | 80% | IN PROGRESS
Copy ASM access from existing signatory | ORIGINAL | APPROVED | 2021-08-27 | 2021-08-27 | 0.6 | 9 | Hemalatha Polasani | MUST | 80% | IN PROGRESS
Holiday |  |  | 2021-08-30 | 2021-08-30 | 0
1. Process Copy action and 2. Check if copy action was successful for all objects | ORIGINAL | APPROVED | 2021-08-31 | 2021-08-31 | 0.6 | 9 | Hemalatha Polasani | MUST
Remove Signatory | ORIGINAL | APPROVED | 2021-09-01 | 2021-09-01 | 0.6 | 9 | Hemalatha Polasani | MUST
1. Verify and adjust “PO owner flag” for signatory and 2. Check if remove action was successful for all objects | ORIGINAL | APPROVED | 2021-09-02 | 2021-09-02 | 0.6 | 9 | Hemalatha Polasani | MUST
Delete Object and Grouped objects | ORIGINAL | APPROVED | 2021-09-03 | 2021-09-03 | 0.6 | 9 | Hemalatha Polasani | MUST
Process Finalisation and Exception handling | ORIGINAL | APPROVED | 2021-09-06 | 2021-09-07 | 1.2 | 18 | Hemalatha Polasani | MUST
Business demo | ORIGINAL | APPROVED | 2021-09-08 | 2021-09-08 | 0.6 | 9 | Hemalatha Polasani | MUST
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0